Norton in Bloom Action list 2018

Version 1.4  March 2018

Action list of items to be covered/considered for In Bloom competition 2018.

* - indicates a change

| Item | Description |  | Action by | date requd |
| --- | --- | --- | --- | --- |
| Judging |  |  |  |  |
| Judging Route Method of transport Itinerary leaflet | Village Hall to P Pool, big green to rec. ground, church, village centre then back to start. Car Description of route, meeting points |  | Veronica |  |
| Judges Meeting point Book room Refreshments Introductions Presentation Tour guides (2) | Village Hall 15 mins powerpoint Ann to check with HOE in Bloom if she can lead. | * | Malcolm Ann H Chris Malcolm Ann |  |
| Tour End point Refreshments | Village Hall |  |  |  |
| Village theme 2018 | Nature in Habitats. |  |  |  |
| Spring seminar | Eventually established to be on 22 March at Upton, | * |  |  |
| Portfolio Contents Photos Dropbox for photos Printing and despatch | Collation and printing. Useful for Chris G and Chris W also | * | Chris Malcolm and others. Malcolm Chris |  |
| Information boards | For the judge’s presentation. Use press cuttings, posters etc. |  | Please save cuttings. | Malcolm |
| Work items |  |  |  |  |
| Working parties | Hartley bed, Napeley corner and new bed. 12th March. Parton’s P 2nd May 10.00am , rebuild steps etc. | * * | All available. Bill costs to Group |  |
| School frontage | Provide 3 more planters from big green |  |  |  |
| Fences/tubs | Remove, move or store surplus tubs. Pub move and group. Brook farm. Plant with sedums etc. in scree. Griffin. Use grasses and geraniums. Church walks. Bedding. Chapel Lane. ?? Replace compost in the remainder. Apply preservative/paint |  |  |  |
| Summer planting scheme | Ann has determined the scheme and will complete an order. Malcolm to circulate the plant list to people on the distribution list for them to include personal orders. | * | Ann Malcolm | x |
| Partons Pool | Wkg party 2nd May | * | All available |  |
| Wildflower sowing | Remote graveyard. Order seeds Dig area in advance of sowing. Chris will also donate seed. | * | Malcolm |  |
| Rec ground | Jim and Lyn to maintain, buying new plants as required. |  |  |  |
| Horsewash | Plants as necessary to make impact. | * |  |  |
| Village Hall | Remove barrel when flowering finished. Provide trellis on the wall behind planters | * |  |  |
| Church bed | Was replanted last year. |  | Judith H |  |
| Hartley bed | Sort and buy new plants. |  | W.P. |  |
| Jubilee bed | Spray area under shrubs with roundup. Under plant as appropriate through the seasons. | * | Ann |  |
| Bradling stone/planters | Incorporate the 2 barrels into the overall planting scheme. |  |  |  |
| Mary Keay bed | Replant as necessary. |  | Fiona |  |
| ‘Barbara’s bed’ |  |  | Barbara |  |
| Plough. |  |  |  |  |
| ‘Joans corner.’ | Bedding plants |  | Sally |  |
| ‘ Mel’s wall’ - Lavender | Renew the lavender plants. |  |  |  |
| Napeley Dv corner | Incorporate more grasses. |  |  |  |
| Make new beds | On the large green, to replace barrels. Planting? |  | Working party |  |
| Road signs | Planting schemes |  |  |  |
| Remote graveyard | Provide wildflower bed. |  |  |  |
| Planting for spring | Wallflowers and tulips overwintering. These should suffice. |  |  |  |
| Street weeding |  |  |  |  |
| Street cleaning |  |  |  |  |
| Litter picking | See minutes | * |  |  |
| Recycling Council Group |  |  |  |  |
| Water sources | It was suggested that the pub might be willing to allow barrels to be topped up with their supply occasionally. | * | To be followed up |  |
| Watering schedule | Watering responsibilities had been revised. | * | Carol |  |
| Heritage |  |  |  |  |
| Footpaths | Info and photos needed from the footpath group. |  | Text received from DR, await photos |  |
| Events |  |  |  |  |
| Open gardens | Sunday 24th June Publicity asking for gardens Open gardens publicity – not Fbook Refreshment venues Treasure Hunt Transport? Route leaflet |  | Note to go in April Messenger asking for gardens. | Chris/M |
| Bat/moth walk | Provisional date of 7th Sept not favoured at the meeting. Secy has emailed members asking for direction. | * |  |  |
| Bat talk. | Talk arranged for Thursday 24th May, village hall, 7.30. Free but pay £1 for cup of tea. Hall is booked. | * |  |  |
| Hodnet Hall visit. | Arranged for 11th May. Afternoon preferred, 2.00pm, teas if possible. Cost £7. Messenger and media publicity. Booking and arranging lifts, | * | Ann Chris, Malcolm Malcolm |  |
| Village show | Manager Committee: Ann H, Veronica, Bev & Carol, Malcolm, Joseph. Date 1st September. Hall booked for Fri eve and Sat. | * |  |  |
| Village show schedule | Completed . | * |  |  |  |
| Publicity Village Press TV Displays | Messenger Facebook See minutes. Website/email list Leaflets Posters Show printing Press release once theme agreed and ongoing. | * | Chris Lucy Malcolm Veronica “ “ Nigel |  |
| Special leaflet drop | To cover 3 forthcoming events | * | Chis |  |
| Community service |  |  |  |  |
| Funding Council Fundraising events Sponsorship | PC Awaiting confirmation £875 Hinds Head – meetings. Shepleys Butchers Peake Decorators |  |  |  |