## Telescopic legs (Wk3-5, Strat1)
Telescopic Legs (Weeks 3-5, Strategy 1)
Components | Risks |  |  | Countermeasures | Reference | Note | Purchase | Risk
| Manufacturing | Assembly | Others
Leadscrew | NIL (Will be bought online. Really cheap only $10) | Backlash between leadscrew and slider |  | 1. Preload by using two nuts, each in contact with one surface of the screw thread. To prevent small positioning irregularities due thermal effects, I will be trying out an easily replacable plastic nut and a steel leadscrew. Another mechanical option will be to use anti-backlash nuts such as this one: https://www.google.com/search?q=self+adjusting+anti+backlash+nuts&oq=self+adjusting+anti+backlash+nuts&aqs=chrome..69i57&sourceid=chrome&ie=UTF-8#q=self+adjusting+anti+backlash+nuts&tbm=shop&* 2. Compensate for backlash by accounting for it in programming. If I can find out the amount of backlash, and I know which side of the screw thread is contacting the nut thread, it is possible to simply substract out the backlash. | http://www.liutaiomottola.com/Tools/Backlash.htm | Buy leadscrew 8mm diameter, 2 or 4mm pitch (check if pitch or lead) | http://www.ebay.com/itm/T8-600mm-Stainless-Steel-Lead-Screw-with-Mounted-Ball-Bearing-and-Shaft-Coupling/252492860075?_trksid=p2047675.c100005.m1851&_trkparms=aid%3D222007%26algo%3DSIC.MBE%26ao%3D2%26asc%3D20131003132420%26meid%3D668be17844e04c67ae2c46c36124bd82%26pid%3D100005%26rk%3D3%26rkt%3D6%26sd%3D272334634395 http://www.banggood.com/T8-Anti-Backlash-Spring-Loaded-Nut-For-2mm-8mm-Acme-Threaded-Rod-Lead-Screws-p-1111893.html?rmmds=detail-left-hotproducts | Need to use at least 2 pieces of plywood for slider
Motor | NIL (already have a NEMA 17) | Misalignment with leadscrew is larger than what WAC 20 can handle |  | Minimize horizontal errors to ensure better alignment
Coupler | NIL (will buy the WAC 20) | Need to find appropriate diameter for both sides of coupling |  |  |  | Buy 8mm to NEMA 17
Legs | Unable to find a cheap telescopic leg online | If manufacturing, need to ensure sliding contact. |  | Might consider using scissor linkages if telescopic legs too hard to manufacturing/buy
Table |  | Final table assembly is not horizontal. |  | Use brackets. Draw positions of bracket holes. Tap holes. Drill holes.
Slider
Wiring |  |  |  | Will cable tie wires and stow inside electrical box (acrylic/wood)
Rails | Rails not cut to size | Rails not glued parallel |  | 1. File down inner part of rail 2. Make slider bigger 3. Draw lines for position of rail before gluing. |  | Limit clamping force when letting glue cure

## Scissor Linkage (PUPS #5)
Scissor Linkages (see PUPS #5 Concept 2 and 3)
Components | Risks |  |  | Countermeasures | Reference | Note | Purchase | Risk
| Manufacturing | Assembly | Others
Leadscrew | NIL (Will be bought online. Really cheap only $10) | Backlash between leadscrew and slider |  | 1. Preload by using two nuts, each in contact with one surface of the screw thread. To prevent small positioning irregularities due thermal effects, I will be trying out an easily replacable plastic nut and a steel leadscrew. Another mechanical option will be to use anti-backlash nuts such as this one: https://www.google.com/search?q=self+adjusting+anti+backlash+nuts&oq=self+adjusting+anti+backlash+nuts&aqs=chrome..69i57&sourceid=chrome&ie=UTF-8#q=self+adjusting+anti+backlash+nuts&tbm=shop&* 2. Compensate for backlash by accounting for it in programming. If I can find out the amount of backlash, and I know which side of the screw thread is contacting the nut thread, it is possible to simply substract out the backlash. | http://www.liutaiomottola.com/Tools/Backlash.htm | Buy leadscrew 8mm diameter, 2 or 4mm pitch (check if pitch or lead) | http://www.ebay.com/itm/T8-600mm-Stainless-Steel-Lead-Screw-with-Mounted-Ball-Bearing-and-Shaft-Coupling/252492860075?_trksid=p2047675.c100005.m1851&_trkparms=aid%3D222007%26algo%3DSIC.MBE%26ao%3D2%26asc%3D20131003132420%26meid%3D668be17844e04c67ae2c46c36124bd82%26pid%3D100005%26rk%3D3%26rkt%3D6%26sd%3D272334634395 http://www.banggood.com/T8-Anti-Backlash-Spring-Loaded-Nut-For-2mm-8mm-Acme-Threaded-Rod-Lead-Screws-p-1111893.html?rmmds=detail-left-hotproducts | Need to use at least 2 pieces of plywood for slider
Motor | NIL (already have a NEMA 17) | Misalignment with leadscrew is larger than what WAC 20 can handle |  | Minimize horizontal errors to ensure better alignment
Coupler | NIL (will buy the WAC 20) | Need to find appropriate diameter for both sides of coupling |  |  |  | Buy 8mm to NEMA 17
Scissor linkages | Laser cutter might not give us the precision we need. Need to experiment and try |  |  | Laser cut smaller than dimension. Use precision tools to make finer dimensions. |  | Laser cut scissor linkages next week. Materials need: dowel pins, piece of plywood
Table |  | Final table assembly is not horizontal. |  | Use brackets. Draw positions of bracket holes. Tap holes. Drill holes.
Wiring |  |  |  | Will cable tie wires and stow inside electrical box (acrylic/wood)
Gears |  | Backlash |  | Ensure mesh at pitch diameters

## Miscellaneous
http://www.tmart.com/Pro-M5-Blood-Pressure-Oxygen-Heart-Rate-Monitor-Fitness-Tracker-Bluetooth-Smart-Wrist-Band-Bracelet-Black_p354800.html