## Sheet1
WBS Diagram for Project "Plan Parade"
1.0 Parade Planned
2.0 Assemble all Documents
| 3.1 Participants Finalized |  |  | 3.2 Safety/ Security Arranged |  | 3.3 Permits Ready | This is the lowest level of WBS, consisting of deliverable Work Packages. Deliverable items. This is the level where Time and Cost are managed.
3.1.1 Obtain Floats | 3.1.2 Arrange Bands | 3.1.3 Get Clowns | 3.2.1 Organize Security |  | 3.2.2 Arrange First Aid | 3.3.1 Get Permits | This is a level of further decomposition into Activities. Things to do. Discussed in the 'Time' Steps