## Risk Register
| Project | Project Name
| Code # | Project Code
| Contract # | Contract No.
| Data Date | Data Date
ID | T/O | Title | Probability | Schedule | Cost | Safety | Rank | ID | T/O | Response | Action | Total Cost | Owner | Description | ID | T/O | Cause | Impact | Status | Manageability | Start | Finish
1 | T | Finding Rock Cavities | M | H | M | VH | 40 | 1 | T | Reduce |  |  | Con. |  | 1 | T |  |  | Managed | Moderate
2 | O | [5 empty] | 0 | 2 | O | [5 empty] | 2 | O
3 | T | [5 empty] | 0 | 3 | T | [5 empty] | 3 | T
4 | [6 empty] | 0 | 4 | [6 empty] | 4
0
0
0
0
0
0
0
0
0
0
0
0
0
PROBABILITY & IMPACT MATRIX
|  |  | T/O | Threat/ Opportunity
|  |  |  | Probability | Schedule | Cost
|  |  | VH | > 70% | >150 | > 500,000 QR
|  |  | H | 50% to 70% | 50 to 150 | 100,000 to 500,000
|  |  | M | 30% to 50% | 20 to 50 | 50,000 to 100,000
|  |  | L | 10% to 30% | 10 to 20 | 10,000 to 50,000
|  |  | VL | up to 10% | <10 | <10,000 QR
N

## Labels
ID | T/O | Title | Probability | Schedule | Cost | Safety | Rank | Response | Action | Total Cost | Owner | Description | Cause | Impact | Status | Manageability | Start | Finish
| T |  | VH | VH | VH | VH |  | Avoid |  |  | PM |  |  |  | Open | Easy
| O |  | H | H | H | H |  | Transfer |  |  | Emp. |  |  |  | Proposed | Moderate
|  |  | M | M | M | M |  | Reduce |  |  | Con. |  |  |  | Rejected | Difficult
|  |  | L | L | L | L |  | Accept |  |  | Eng. |  |  |  | Managed
|  |  | VL | VL | VL | VL |  | Exploit | [6 empty] | Impacted
|  |  | N | N | N | N |  | Faciltate | [6 empty] | Deleted
Exploit
Transfer
T/O:
Threat
Opportunity |  |  |  | Prob | Impact
[5 empty] | VL | L | M | H | VH
Probability: |  |  |  | VH | 5 | 9 | 18 | 36 | 72
VH | Very High | > 70% |  | H | 4 | 7 | 14 | 28 | 56
H | High | 50% to 70% |  | M | 3 | 5 | 10 | 20 | 40
M | Medium | 30% to 50% |  | L | 2 | 3 | 6 | 12 | 24
L | Low | 10% to 30% |  | VL | 1 | 1 | 2 | 4 | 8
VL | Very Low | up to 10%
N | Negligible
Impact |  |  |  |  | 1 | 2 | 4 | 8 | 16
Schedule |  |  |  | 4.5 | 4.5 | 9 | 18 | 36 | 72
VH | Very High | >150 |  | 3.5 | 3.5 | 7 | 14 | 28 | 56
H | High | 50 to 150 |  | 2.5 | 2.5 | 5 | 10 | 20 | 40
M | Medium | 20 to 50 |  | 1.5 | 1.5 | 3 | 6 | 12 | 24
L | Low | 10 to 20 |  | 0.5 | 0.5 | 1 | 2 | 4 | 8
VL | Very Low | <10
N | Negligible
Cost
VH | Very High | > 500,000 QR
H | High | 100,000 to 500,000
M | Medium | 50,000 to 100,000
L | Low | 10,000 to 50,000
VL | Very Low | <10,000 QR
N | Negligible
Response
Threat
Avoid
Transfer
Reduce
Accept
Opportunity
Exploit
Faciltate
Exploit
Transfer
Owner
PM | Project Manager
Emp. | Employee
Con. | Contractor
Eng. | Engineer
Status
Open
Proposed
Rejected |  | (Closed)
Managed |  | (Closed)
Impacted |  | (Closed)
Deleted
Manageability
Easy
Moderate
Difficult